## Slide 1: ERP Implementation Strategies
Sujoy Mukhopadhyay
Paul Xie
Carlos Romero

## Slide 2: Introduction
ERP implementation – installation of a software package that integrates all data and processes into a centralized, unified database.
Cross functional and company wide
Organizations rely on software for cohesiveness
Can lead to cost savings, more efficient processes

## Slide 3: Different Implementation Methodologies
Depends on several factors
  Size, industry, sales volume
Common basic factors
  Physical Scope, BPR, Resource Allocation
3 Broad implementation strategies
  Big Bang, Middle-road, Vanilla

## Slide 4: Things to Consider
Must first define business objectives
  High maintenance costs, Mergers & Acquisitions, Compliance
Vendor selection
  Evaluated on functionality AND ability to achieve business objective
  How involved is the provider with the organization?
  Risk analysis: References, track record
  Written profile

## Slide 5: Alternative Approach
Alternative Approach
  Stick to deadlines, deal with issues/problems as they arise
Traditional Approach
  Fix all the “bugs” before rolling out the system

## Slide 6: Alternative Approach
Advantages
Disadvantages
Eliminates possibility of going over budget, missing deadlines
Can create ownership, allows for buy in
Success depends on org.’s ability to embrace & adapt to change
No one likes change
Problems in system can discourage employees
Lower morale, productivity, efficiency
Constant change leads to frustration
Flawed system increases business risk

## Slide 7: The “Big Bang”
--- What is the “Big Bang” approach?
-- A straightforward ERP Implementation approach. It means all ERP modules, such as financials, manufacturing, and human resources, etc, are implemented in all business units at all geographic locations at the same time.
-- It will push the entire organization to use the new system at the same time.
-- The old system will be entirely shut down.

## Slide 8: The Big Bang Advantages
1)The entire organization reaps the benefits of the deployed system as this enforces process change.
2) Installing the ERP by Big bang approach may help the company to get quicker return on the investment.
3) Easier integration and reporting.
4) No temporary interfaces required.
5) Lower cost of running the systems as legacy systems are retired simultaneously.
6) Faster implementation timeline.

## Slide 9: Disadvantages
1) High capital and human resource investment.
2) Any technical performance issue affects the entire user population.
3) Requires training of the entire user population.
4) Complex deployment and testing.
5) The completeness and validity of the converted data is not completely proved, only in the pre-phases, but not in the whole system situation.
6) This adoption of the new system is vulnerable because of the limited possibilities to maneuver, and there is a lot of pressure because the deadline must be met.

## Slide 10: Implementation Processes
--- Converting the system.
-- Planning, convert data from old system, load data in new system, test data in new system, execute off-line trials, and check to verify validity.
--- Releasing parts of the system.
-- Release converted database, release produced application, release infrastructure.
--- Training the future users.
-- Create main buffer of experienced staff, training all users.
--- Releasing the whole system.
-- Turn down the old system and load the new system.

## Slide 11
Global
Requirements
Gathering
Global
Design and
Base Design
Template
Base Design
Configuration
And Development
Region
Specific
Delta Design
Region
Specific
Configuration
And Development
Region
Specific
Delta Design
Region
Specific
Configuration
And Development
Region
Specific
Delta Design
Region
Specific
Configuration
And Development
Region
Specific
Delta Design
Region
Specific
Configuration
And Development
Testing and
Deployment
Cut Over
And
Go-live
All Modules
Implemented
In all countries/regions

## Slide 12: Who should choose the “Big bang”?
-- The Big bang is difficult to manage for very large organizations.
-- It is easier in organizations that are centralized.
-- It is less risky with simple processes.
-- It is easier for small, simple organizations.

## Slide 13: Middle-Road Approach
Physical Scope (Medium)
  Less than half of total company sites
  Gauge user acceptance
  Test in “real world” environment
  Reduced risk

## Slide 14: Middle-Road Approach
BPR Scope (Medium)
  Few changes to existing business processes
  Less impact to external parties
  Less training
  Shorter timeline

## Slide 15: Middle-Road Approach
Technical Scope (Medium)
  Limited customization
  Easier upgrades and support
  Reduced risk of knowledge loss when key employees leave

## Slide 16: Middle-Road Approach
Module Implementation (“ala carte”)
  Not all ERP modules are implemented
  Industry specific modules and sub modules can be chosen
  Some legacy systems to remain functional

## Slide 17: Middle-Road Approach
Resource Scope (Medium)
  Training and costs are balanced between Comprehensive (Big Bang) and Vanilla approach

## Slide 18: Vanilla Approach
Physical Scope (Low)
  Deployment locations are extremely limited
  Typically involves less than 100 users
  May not be able to detect issues related to capacity

## Slide 19: Vanilla Approach
BPR Scope (Low)
  Few areas are affected, therefore little change is needed
  Shorter timeline
  Processes may not exactly match ERP model

## Slide 20: Vanilla Approach
Technical Scope (Low)
  No modification or customization to software
  Easy upgrades and support

## Slide 21: Vanilla Approach
Module Implementation (Skeletal)
  Only essential modules are chosen
  Industry specific modules are discouraged
  Minimized risk

## Slide 22: Vanilla Approach
Resource Scope (Low)
  Less training
  Shorter timelines
  Least cost

## Slide 23: ERP Implementation Strategies
 | Physical Scope | BPR Scope | Technical Scope | Modules | Resources
Big Bang | All | High | High | Full | High
Middle Road | Some | Medium | Medium | A la Carte | Medium
Vanilla | Very Few | Low | Low | Skeletal | Low

## Slide 24: Questions?