## Slide 1
In Progress
Configuration
  Participate and Complete UAT Test Scripts & Business Processes
  Refining Roles and Permissions Based on Testing
  Validate and Test Configuration Change Requests
Delegation of Authority (DOA)
  Complete DOA Import File
  Attend DOA360 Training
  Run Sample DOA Import
Supplier
  Complete Supplier Analysis and Cleanse for All BU SetIDs
  Send Supplier Round 1 Invitation Announcements and Invites
  Extend CSU Network Suppliers to Acceleration Campus
Training and Demos
  Conduct End User and Admin Approver Demos
  Communicating to Campus Stakeholder Groups
  (meetings, website, portal announcements)
Recently Completed
Procure-to-Pay (P2P) Objectives
Implement strategic, standardized process
Increase efficiencies by eliminating manual touchpoints
Mitigate risk and increase cost savings
p2p.calstate.edu
Risks
Resource constraints with multiple competing priorities (CSUBUY, Concur, CHRS Upgrades)
Project communication to campus stakeholders
Chart: 
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Sales | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
63%
Configuration
  Completed Campus Security Roles and Permissions
  Configured CFS and CSUBUY in Preparation for UAT
  Validated and Tested Setup for UAT
Delegation of Authority (DOA)
  Designed and Built DOA Module and Integrations
Supplier
  Sent Supplier Invitation Announcement to Campus
  Attended Supplier Onboarding Training
Training and Demos
  Conducted End User and Admin Approver Demos
  (> 2,000 attendees)
  Reviewed and Modified Training Documentations for UAT
  Attended User Acceptance Testing (UAT) In-Person Workshops
Coming Soon
UAT
  Campus completion of UAT Scripts & Signoff
Configuration
  Analysis of Campus Roles
Training and Demos
  Operational In-Person Campus Trainings
  Campus End User and Approver Training Strategies
  Communicate Campus Cutover Strategy
User Acceptance Testing (UAT) San Jose (North)
September 5-9
Channel Islands (South)
September 15-18